## Sheet1
201 | CHG0054669 | Flight Paper | FlightPaperBLAPI | Flightpaper-webapp_ACM | NA | NA | Yes | Yes | 12 May, 2026 | 13 May, 2026 | Pending | https://dev.azure.com/AirlineOps/AirlineOpsBAU/_workitems/edit/13/ | https://github.com/AirlineOperation/flightpaper-business-api/pull/26 | Yes. | There was one production issue reported where scheduler calling data api is returning error, due to which flightpaper data is not populated in the database. As discussed with team and Dheeraj, we plan to do complete rollback. (webapp already rolled back on friday. Need to rollback API and Mobile app now). | Yes. | CHG0055308, (INC3908772, INC3911012).
|  |  | FlightPaperDALAPI | [6 empty] | 15 May, 2026 |  | https://dev.azure.com/AirlineOps/AirlineOpsBAU/_workitems/edit/367/
|  |  | LandTDALAPI | [8 empty] | https://dev.azure.com/AirlineOps/AirlineOpsBAU/_workitems/edit/5869/ | https://github.com/AirlineOperation/flightpaper-webapp/pull/16
https://dev.azure.com/AirlineOps/AirlineOpsBAU/_workitems/edit/11493/
https://github.com/AirlineOperation/flightpaper-data-api/pull/15
https://github.com/AirlineOperation/lnt-data-api/pull/18
204 | CHG0055117 | eGCA | EGCA_BLAPI_ACM | EGCAAPP_ACM | NA | NA | Yes | Yes | 13 May, 2026 | 15 May, 2026 | Pending | Flight restriction api modified, new trainers logbook api added.pdf generation logic added.handled crew changes while doing core verifier refresh | https://github.com/AirlineOperation/egca-business-api/pull/378 | Release/US-233-7024-7370 | CTASK0056217 | Yes. This is a request for rollback approval for CMR CHG0055117. The newly deployed report functionality is currently failing due to the absence of a required AIMS production table.
|  |  | EGCA_DataLayerAPI_ACM | [10 empty] | Release/US-233-7024-7370
|  |  | GCA_AIMSDataAccess_ACM | [8 empty] | Fetching data from egca db through trainers logbook api | https://github.com/AirlineOperation/egca-data-api/pull/247 | Release/US-7024 |  | The stored procedures developed as part of this user story were successfully validated, and the functionality is working as expected in UAT, where it has been tested jointly by me and the UAT team, with QA and UAT sign-offs in place. However, post-deployment, the issue was observed in production as the required database table is not present.
[12 empty] | Fetching simulator data and crew training qulaification data from AIMS db |  | Release/US-233-7024-7370
[13 empty] | https://github.com/AirlineOperation/egca-aims-data-api/pull/47 |  |  | While this is being reviewed with DB support (Anurag Kapoor is coordinating), we request your approval to proceed with the rollback to ensure system stability.
[12 empty] | Trainers logbook report added.handled crew changes while doing core verifier refresh screen | https://github.com/AirlineOperation/egca-web-ui/pull/252 |  |  | Kindly provide your approval at the earliest
209 | CHG0054330 | 6e Digi Breath analyser | flightsafety-pfmc-api_ACM | NA | NA | NA | No | No |  | 14 May, 2026 | Pending |  |  | Yes (CTASK0055963) | we have successfully deployed the CR last night. However, there was a small change where we have been asked to restrict triggering of SMS for Home standby crew. Requesting your support in executing the pipeline. | No. Updating the last change with a new pipeline has to be triggered. | No
barosterapi_ACM
231 | CHG0055607 | 6e IndiGo Access | 1.releases/bookingwidget-b2b-ms/1.0.1 | NA | NA | NA | No | No | 02 June, 2026 | 04 June, 2026 | Completed |  |  | Yes, | This CMR was implemented from 4th june 26 to 5th June 26. During this CMR (INC3990956) this incident was logged. App team asked us to push a new pipeline to resolve the issue. CTASK was assigned to the OCP Bin - CTASK0057069. we deployed the changes. | No | (INC3990956)
2.releases/agentbooking-b2b-ms/0.0.9
3.releases/prepayment-b2b-ms/1.0.0
4.releases/mybooking-b2b-ms/0.0.7
5.releases/itinerary-b2b-ms/1.0.2
259 | CHG0055985 CHG0055986 | 6e Skyplus | releases/FlightUpgradeCS/1.0.9 | releases/search-results/3.3.5 | releases/loyalty-event-consumer/1.0.0 | NA | Yes | Yes | 22nd June, 2026 | 25th June, 2026 | Completed |  |  | Yes | The implementation of Plan B handling for IBC/IBC voucher bookings via CHG0055985-POD-29249, which enabled voucher validity extension via Loyalty (Capillary) integration, led to performance degradation and intermittent failures on the IndiGo payment page. As a result, the solution was rolled back. The underlying root cause of these issues remains unidentified and requires detailed investigation by the WNM team along with the Capillary vendor. CHG0055985 was rolled back by Loyalty/Capillary team to resolve the P1. | Yes | INC4077854 (P1)
|  |  | releases/FlightUpgradeIBC/1.0.4 | releases/addon-revamp/1.1.4
|  |  | releases/planbeligibilty/1.0.11 | releases/fare-summary/3.2.8
|  |  | releases/gdpr/1.0.8 | releases/passenger-edit/3.4.1
|  |  | releases/flightsearch/1.0.59 | releases/trip-summary/3.3.7
|  |  | releases/bookingwidgets/1.0.43 | releases/seat-selection/3.3.2
|  |  | releases/lowfarecalendar-worker/1.0.0 | releases/retrieve-pnr/3.3.0
|  |  | releases/addonpost/1.0.24 | releases/status-results/1.0.4
|  |  | releases/CustomBundles/1.0.7 | releases/booking/3.2.8
|  |  | releases/passengersget/1.0.25 | releases/loyalty-dashboard/1.1.7
|  |  | releases/passengersssr/1.0.43 | releases/web-checkin/2.3.2
|  |  | releases/reviewsummary/1.0.42 | releases/refund/3.1.3
|  |  | releases/seatselection/1.0.28 | releases/agentic-workflows/1.0.1
|  |  | releases/seatsell/1.0.9 | releases/itinerary/3.4.6
releases/passengerspost/1.0.23
releases/itinerary-save/1.0.46
releases/loyalty/1.0.36
releases/loyalty-event-consumer/1.0.0
releases/FlightStatus/1.0.5
releases/checkin/1.0.40
releases/checkin-eventprocessor/1.0.1
releases/web-check-in-agent/1.0.4
releases/prepayment/1.0.45
releases/itinerary/1.0.73
261 | CHG0056120 & CHG0056121 | 6e partner | MS: | MF: | NA | NA | NA | NA |  | 24 June, 2026 | Completed |  |  | Yes. | Split PNR functionality is not working, getting an error while clicking on it. Under the CTASK - CTASK0058245, fixes were implemented. MF to be deploy: |  | INC4099277
|  |  | releases/postpayment-b2b-ms/0.0.9 | b2b-releases/addon/1.1.7 | [5 empty] | 29 June, 2026
|  |  | releases/reviewsummary-b2b/1.0.1 | b2b-releases/booking/1.1.1 | [10 empty] | JIRA ID: STRAW-4682¦ INC4099277 INC4099277 - Split PNR functionality is not working, getting an error while clicking on it.
|  |  | releases/itinerary-b2b-ms/1.0.3 | b2b-releases/clients-and-quotations/1.0.7
|  |  | releases/addonget-b2b-ms/1.0.1 MS: | b2b-releases/fare-summary/1.1.5 | [10 empty] | MF: b2b-releases/split-pnr/1.0.6
|  |  | releases/addonget-b2b-ms/1.0.1 | b2b-releases/passenger-edit/1.1.5
|  |  | releases/seatselection-b2b-ms/0.0.8 | b2b-releases/itinerary/1.1.8 | [10 empty] | MF PR: https://github.com/CommericalWebsite/6eAgent_React_MF/pull/1920
|  |  | releases/seatsell-b2b-ms/0.0.4 | b2b-releases/login/1.1.2
|  |  | releases/account-b2b-ms/0.0.9 | b2b-releases/search-results/1.1.6
|  |  | releases/dotrez-b2b-ms/1.0.1"" | b2b-releases/seat-selection/1.1.4
|  |  | releases/flightsearch-b2b-ms/1.0.5 | b2b-releases/split-pnr/1.0.6
|  |  | releases/flightsell-b2b-ms/0.0.9 | b2b-releases/user-profile/1.1.3
|  |  | releases/itinerary-b2b-ms/1.0.3 | MF:
|  |  | releases/bookingwidget-b2b-ms/1.0.2 | b2b-releases/addon/1.1.7
b2b-releases/seat-selection/1.1.4
b2b-releases/search-results/1.1.6
b2b-releases/fare-summary/1.1.5
b2b-releases/itinerary/1.1.8
b2b-releases/passenger-edit/1.1.5